## KPIs
metric | value
total_tasks | 4
completed_count | 0
open_count | 4
overdue_count | 1
on_time_delivery_pct | N/A
avg_open_age_days | 8.5

## RAG
project | rag | overdue_ratio | blocked_ratio
Alpha | Amber | 0.2 | 0.2
Beta | Green | 0 | 0

## Overdue
task_id | project | owner | status | priority | due_date | days_overdue
T-900 | Alpha | Rashed | In Progress | High | 2026-01-10 | 5

## RAID
project | owner | raid_type | raid_description
Alpha | Rashed | Risk | Vendor response may delay milestone.

## Executive_Summary
Executive Summary
As of 2026-01-15, the portfolio contains 2 projects and 4 tasks; 1 task is overdue. On-time delivery is N/A because there are no completed tasks with a valid completion date.