## Tracker
task_id | project | owner | status | priority | start_date | due_date | completion_date | raid_type | raid_description
M-001 | Alpha | Rashed | In Progress | Critical | 2026-01-01 | 2026-01-10 |  | Risk | Vendor delay may affect milestone
M-002 | Alpha | Nora | Blocked | High | 2026-01-02 | 2026-01-20 |  | Issue | Access approval pending
M-003 | Alpha | Lina | Completed | Medium | 2026-01-01 | 2026-01-08 | 2026-01-08
M-004 | Beta | Omar | Completed | Low | 2026-01-03 | 2026-01-09 | 2026-01-11
M-005 | Beta | Rashed | In Progress | High | 2026-01-05 | 2026-01-28 |  | Dependency | Awaiting upstream data
M-006 | Beta | Nora | Not Started | Medium |  | 2026-02-01